## Comm Plan Exemplar
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Notes
All Departments (IT, Marketing, Finance, etc.) | Project Kickoff Meeting | One-time | Project Sponsor, Project Manager | Sunday at 10 Am to 1 pm | In-person/Online | Align all stakeholders and project team members on project objectives, timelines, roles, and expectations. | Check on the availability of team members beforehand to ensure everyone can attend.
Marketing Manager | Marketing Campaign Meeting | Bi-Weekly ( 2 times a week ) | Marketing Team & Design Team | 2 times a week | In Person/ Video Conference | Track progress, address challenges, and ensure all team members are aligned with the campaign strategy. | Ensure all relevant data is shared in advance with the team to allow for productive discussions.
HR manager | Emails, internal meetings | Monthly | HR Team | once a month | Emails, internal meetings | Team engagement activities, feedback | Organize team-building events
IT Manager | Website Upgrade Status | Weekly | Marketing Team, Design Team | Tuesdays at 9 Am | Ib person / Daily email updates | Provide updates and keep the teams aligned on the technical progress of the website upgrade. | Include any technical challenges encountered during the week and their proposed solutions.
Luxury Brand Partners & PR Manager | Partnership Contracts Check | Bi-weekly | Marketing Manager | Every other Monday | In-Person/Email | Review partnership agreements to ensure they align with the company’s luxury experience goals. | Schedule individual follow-ups if any brand partners have specific concerns.
Customer Service Manager , HR Manager | Training Program Update | Weekly | L&D Team | Every Monday, 10 AM | In-Person | Ensure customer service team members are on track with their training program. | Check on the availability of team members beforehand to ensure everyone can attend.
PR Manager & Marketing Team | Creative Review Session | One-time | Marketing Manager | Two weeks before campaign launch | In Person | Finalize creative materials for marketing, ensuring they meet luxury standards. | Add final adjustments as needed based on the feedback from the session.
Project Manager | Budget Status Update | Bi-weekly | Finance Manager | Every other Sunday, 1 PM | Email / In person | Monitor and report financial status to ensure budget alignment with project goals. | Include detailed breakdowns of any unexpected expenses or savings in the report.
Project Sponsor | Project Overview and Updates | Monthly | Project Manager | Every other Monday, 9 AM | In-Person Meeting | Provide overall updates on the project to the sponsor and address high-level concerns. | Prepare a summary of any key challenges or risks that need sponsor intervention.
Project Manager | Training Completion Survey | One time | HR Manager | One week after training ends | Email | Collect feedback from participants to evaluate the success of the training program and identify areas for improvement.