## GANTT Chart
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3
[7 empty] | Dec | [22 empty] | Jan | [21 empty] | Feb
[7 empty] | S | M | T | W | Th | S | M | T | W | TH | S | M | T | W | TH | S | M | T | W | TH | S | M | T | W | TH | S | M | T | W | TH | S | M | T | W | TH | S | M | T | W | TH | S | M | T | W | TH | S | M | T | W | TH | S | M | T | W | TH | S | M | T | W | TH
1 | Website |  | 2024-12-01 | 2024-01-02 | 26 day |  | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20
1.1 | Define website requirements | IT & Markeing | 2024-12-01 | 2024-12-10 | 7 days | 0% | bar: Dec S 1 to Dec T 10
1.2 | Create design mockups | IT Manager | 2024-12-10 | 2024-12-29 | 14 days | 0% | bar: Dec T 10 to Dec S 29
1.3 | Perform user acceptance testing | IT & Markeing | 2024-12-29 | 2024-01-02 | 5 days | 0% | bar: Dec S 29 to Jan TH 2
2 | Marketing |  | 2024-01-02 | 2024-02-20 | 36 Day
2.1 | Define target audience | Marketing Manager | 2024-01-02 | 2024-01-02 | 1 Day | 0% | bar: Jan TH 2
2.2 | Conduct social media content |  | 2024-01-02 | 2024-02-12 | 30 day | 0% | bar: Jan TH 2 to Feb W 12
2.3 | Analyze campaign effectiveness |  | 2024-02-13 | 2024-02-20 | 5 days | 0% | bar: Feb TH 13 to Feb TH 20
3 | Training |  | 2024-12-01 | 2024-12-29 | 26 day
3.1 | Develop training materials | L&D Team | 2024-12-01 | 2024-12-01 | 1 day | 0% | bar: Dec S 1
3.2 | Training Program Implementation | Training Manager | 2024-12-02 | 2024-12-22 | 15 day | 0% | bar: Dec M 2 to Dec S 22
3.3 | Monitor progress and improve training processes | CS Manager | 2024-12-16 | 2024-12-29 | 10 days | 0% | bar: Dec M 16 to Dec S 29
4 | Partnerships with Luxury Brands |  | 2024-12-01 | 2024-01-13 | 32 day
4.1 | Pre Plan & Research | PR Manager | 2024-12-01 | 2024-12-15 | 11 day | 0% | bar: Dec S 1 to Dec S 15
4.2 | Develop outreach materials |  | 2024-12-16 | 2024-12-24 | 7 Days | 0% | bar: Dec M 16 to Dec T 24
4.3 | Draft partnership agreements | Legal manager | 2024-12-25 | 2024-01-13 | 14 day | 0% | bar: Dec W 25 to Jan M 13