## Template - Phase 1
R - Responsible | Completes the deliverable or task.
A - Accountable | Makes final decisions and signs off on task completion. Only 1 per task.
C - Consulted | An advisor, stakeholder, or subject matter expert who offers guidance before an action is taken.
I - Informed | Kept up to date on decisions made.
Nefer Tour | It Manager | Marketing Manager | Marketing Team | HR Manager | L&D team | Design Team | Legal manager | PR Manager | Finance Manager | Project Sponsor | Customer Service Manager | Social Media Vendor
PHASE 1
Task/Deliverable
Training program for CS | I | I | I | A | R | I | I | I | I | I | C | I
Website upgrade | A | C | R | I | I | R | I | I | I | I | I | I
Marketing campaign | I | A | R | I | I | C | I | I | I | I | I | R
Partnership Contracts with Luxury Brands | I | C | I | I | I | I | A | R | I | I | I | I