## WBS
Work Breakdown Structure
Milestone | ID | Task | Owner | Duration (days)
Training Program development | 1.1 | Develop training materials | Learning & Development team | 1
| 1.2 | Training Program Implementation | Training Manager | 15
| 1.3 | Monitor progress and improve training processes | Customer service manager | 10
Develop website overview | 3.1 | Define website requirements | It Manager | 7
| 3.2 | Create design mockups | Design Team | 14
| 3.3 | Perform user acceptance testing | It Manager | 5
Marketing Strategy Development | 2.1 | Define target audience | Marketing manager | 1
| 2.2 | Conduct social media content | Vendor with marketing team | 30
| 2.3 | Analyze campaign effectiveness | Marketing manager | 5
Identify Partnerships with Luxury Brands | 4.1 | Create a list of potential partners | PR Manager | 11
| 4.2 | Develop outreach materials | PR Manager | 7
| 4.3 | Draft partnership agreements | Legal manager | 14